## APR-MAY
| Work Breakdown Structure | [8 empty] | Mid-sem evaluation | [7 empty] | Final Submission | Final evaluation
[10 empty] | 2026-06-05 | [7 empty] | 2026-07-27 | 2026-07-31
|  |  |  | Apr 20,2026 | Apr 27, 2026 | May 4, 2026 | MAY 11, 2026 | MAY 18, 2026 | MAY 25, 2026 | JUN 1, 2026 | JUN 8, 2026 | JUN 15, 2026 | JUN 22, 2026 | JUN 29, 2026 | JUL 6, 2026 | JUN 13, 2026 | JUN 20, 2026 | JUN 27, 2026
TASK |  | ASSIGNED TO | START | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
PHASE 1 (PLANNING)
Identify the problem statement |  | All | 2026-04-22
Define project objectives & goals |  | All | 2026-04-22
Determine target users
Define system features |  | Steven&Ray | 2026-04-29
Identify limitations (what is NOT included)
Programming language selection |  | All | 2026-04-29
Database selection |  | All | 2026-04-22
Communication Plan |  | JinHeng | 2026-04-22
Research on Xero |  | Arut | 2026-04-27
Devolep a project timeline/Gantt chart |  | JinHeng | 2026-04-22
Create Github for collaboration
PHASE 2 (ANALYSIS)
Gather functional requirements |  | All | 2026-05-05
Gather non-functional requirements |  | All | 2026-05-05
Create User stories |  | All | 2026-05-06
Create Use Case Diagram |  | All | 2026-05-06
PHASE 3 (DESIGN)
Database Design (ERD, relationships) |  | All | 2026-05-06
Design system flow (miro- flowcharts) |  |  | 2026-05-07
Design Prototype |  |  | 2026-05-08
PHASE 4 (DEVELOPMENT)
Implement database |  |  | 2026-05-11
Implement CRUD operations
Implement pages ( login,dashboard,invoice)
Implement system logic
PHASE 5 (TESTING)
Test individual components( login functions)
Test invoice function(input, expected)
calculate total (match with database)
let supervisor&industry partner test the system
PHASE 6 (DEPLOYMENT)
PHASE 7 (MAINTENANCE)